## Main
Task Name | Estimate time(hours) | Taken by | Actual Time(hours) | Status | Date Doing | Problem
[Review 01] Problem Definition | 0.5 | Hoàng Anh Thắng | 0.5 | Done | 2020-03-31
[Review 01] Customer Request Specification | 2 | Văn Thành Phương Đạt | 1 | Done | 2020-03-31
Total | 2.5 |  | 60% |  | Done task:
[Review 02] Use Case Diagram | 3 | Văn Thành Phương Đạt | 2 | Done | 2020-04-03
[Review 02] Class Diagram | 1.5 | Hoàng Anh Thắng | 1 | Done | 2020-04-04
[Review 02] Sequence Diagram | 4 | Văn Thành Phương Đạt | 5 | Done | 2020-04-04
[Review 02] ERD | 2 | Hoàng Anh Thắng | 1 | Done | 2020-04-03
[Review 02] Entity Description | 1 | Hoàng Anh Thắng | 1 | Done | 2020-04-03
[Review 02] Table Relationship Diagram | 1 | Hoàng Anh Thắng | 2 | Done | 2020-04-04
Total | 12.5 |  | 96% |  | Done task:
[UI Mockup Desktop] Login Screen | 1 | Hoàng Anh Thắng | 1 | Done | 2020-03-31
[UI Mockup Desktop] Home Screen | 1 | Văn Thành Phương Đạt | 1 | Done | 2020-04-01
[UI Mockup Desktop] Car (Item listing) Screen | 2 | Hoàng Anh Thắng | 2.5 | Done | 2020-04-02
[UI Mockup Desktop] Add New Car Screen | 1 | Hoàng Anh Thắng | 2 | Done | 2020-04-02
[UI Mockup Desktop] Edit Car Screen | 1 | Hoàng Anh Thắng | 2 | Done | 2020-04-03
[UI Mockup Desktop] Create New Invoice | 1 | Hoàng Anh Thắng | 5 | Done | 2020-04-04
[UI Mockup Desktop] Category (Item listing) Screen | 1 | Văn Thành Phương Đạt | 0.5 | Done | 2020-04-02
[UI Mockup Desktop] Add New Category Screen | 1 | Văn Thành Phương Đạt | 1 | Done | 2020-04-02
[UI Mockup Desktop] Edit Category Screen | 1 | Văn Thành Phương Đạt | 1 | Done | 2020-04-02
[UI Mockup Desktop] Manufacturer (Item listing) Screen | 1 | Hoàng Anh Thắng | 0.5 | Done | 2020-04-03
[UI Mockup Desktop] Add New Manufacturer Screen | 1 | Hoàng Anh Thắng | 0.5 | Done | 2020-04-03
[UI Mockup Desktop] Edit Manufacturer Screen | 1 | Hoàng Anh Thắng | 0.5 | Done | 2020-04-03
[UI Mockup Desktop] Invoice (Item listing) Screen | 1 | Văn Thành Phương Đạt | 0.5 | Done | 2020-04-03
[UI Mockup Desktop] View Invoice Details Screen | 1 | Văn Thành Phương Đạt | 0.5 | Done | 2020-04-03
[UI Mockup Desktop] View Report Chart Screen | 1 | Văn Thành Phương Đạt | 1 | Done | 2020-04-03
[UI Mockup Desktop] List Customer Screen | 1 | Văn Thành Phương Đạt | 0.5 | Done | 2020-04-03
Total | 17 |  | 117.6% |  | Done task: